## Project schedule
| Europa project | [5 empty] | Project start: | [7 empty] | 2025-05-08
| VanArsdel, Ltd. | Project lead |  |  |  |  | DON’T CHANGE THIS NUMBER | [7 empty] | 1
SIMPLE GANTT CHART by Vertex42.com
| https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html | [5 empty] | 2025-05-05 | [6 empty] | 2025-05-12 | [6 empty] | 2025-05-19 | [6 empty] | 2025-05-26 | [6 empty] | 2025-06-02 | [6 empty] | 2025-06-09 | [6 empty] | 2025-06-16 | [6 empty] | 2025-06-23 | [6 empty] | 2025-06-30 | [6 empty] | 2025-07-07 | [6 empty] | 2025-07-14 | [6 empty] | 2025-07-21 | [6 empty] | 2025-07-28 | [6 empty] | 2025-08-04 | [6 empty] | 2025-08-11 | [6 empty] | 2025-08-18
| Project stages | ASSIGNED TO | PROGRESS | START | END | time axis 2025-05-05 to 2025-08-24
 | time axis 2025-05-05 to 2025-08-24
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
| C1 Developing A Research Question |  |  |  | (criteria)
| Define goals | Abdallah El Sayed | 100% | 2025-05-08 | 2025-05-08 | 1
| Evaluate Research Topics | Abdallah El Sayed | 100% | 2025-05-08 | 2025-05-08 | 1
| Fill out C1 Table | Abdallah El Sayed | 100% | 2025-05-08 | 2025-05-09 | 2
C2 Prepare a Gantt Chart
| Document Tasks/Timing | Abdallah El Sayed | 100% | 2025-05-09 | 2025-05-10 | 2
| Document Tasks/Timing | Abdallah El Sayed | 100% | 2025-05-10 | 2025-05-11 | 2
| Identify Milestones | Abdallah El Sayed | 100% | 2025-05-11 | 2025-05-11 | 1
| Define Dependencies | Abdallah El Sayed | 100% | 2025-05-11 | 2025-05-12 | 2
| Identify Critical Path | Abdallah El Sayed | 100% | 2025-05-12 | 2025-05-12 | 1
C3 Submit Analysis/Design Documentation of Project needs/requirements
| Identify Project Needs from Documentation | Abdallah El Sayed | 100% | 2025-05-12 | 2025-05-12 | 1
| Identify Data requirements, Primary/Secondary | Abdallah El Sayed | 100% | 2025-05-12 | 2025-05-13 | 2
| Identify Solution Scope, Constraints, Requirements | Abdallah El Sayed | 100% | 2025-05-13 | 2025-05-13 | 1
| Understand Skills underpinning Analysis Stage | Abdallah El Sayed | 75% | 2025-05-13 | 2025-05-17 | 5
| Fill out C3 Table/Design Brief | Abdallah El Sayed | 50% | 2025-05-17 | 2025-05-19 | 3
C4 Submit Raw and Cleansed Data
| Identify Data requirements, Primary/Secondary | Abdallah El Sayed | 100% | 2025-05-19 | 2025-05-19 | 1
| Collect/Forge Secondary Data from Listed Sources | Abdallah El Sayed | 100% | 2025-05-19 | 2025-05-20 | 2
| Travel to Relevant Locations | Abdallah El Sayed | 50% | 2025-05-19 | 2025-05-19 | 1
| Collect/Forge Primary Data from Listed Sources | Abdallah El Sayed | 25% | 2025-05-19 | 2025-05-26 | 8
| Develop Survey/Interview Questions | Abdallah El Sayed | 25% | 2025-05-20 | 2025-05-21 | 2
| Conduct Survey(s)/Interviews | Abdallah El Sayed | 0% | 2025-05-21 | 2025-05-31 | 11
| Fill out C4 Table & Excel Spreadsheets | Abdallah El Sayed | 0% | 2025-05-26 | 2025-06-04 | 10
C5 Submit Annotated Diagram/ etc. etc. etc. etc.
| Create Design Folio with 3+ Designs | Abdallah El Sayed | 0% | 2025-06-04 | 2025-06-05 | 2
| Develop Evaluation Criteria for Design | Abdallah El Sayed | 0% | 2025-06-05 | 2025-06-07 | 3
| Produce Infographic Annotated Diagram | Abdallah El Sayed | 0% | 2025-06-07 | 2025-06-09 | 3
| Produce Dynamic Data Visualisations | Abdallah El Sayed | 0% | 2025-06-07 | 2025-06-09 | 3
| Submit Mockups and Layout Diagrams, Formats & Conventions Table, etc. | Abdallah El Sayed | 0% | 2025-06-10 | 2025-06-11 | 2
| Produce Preferred design while applying all appropriate Methods | Abdallah El Sayed | 0% | 2025-06-07 | 2025-06-12 | 6
| Document all Evidence of Critical Thonksing | Abdallah El Sayed | 0% | 2025-06-13 | 2025-06-13 | 1
TERM 2 END SAT 2 BEGINNING
C6 Submit Spreadsheet/SQL/Database And Testplan/Validation
| Set up Database Structure Featuring all Relevant Data Entries | Abdallah El Sayed | 0% | 2025-06-13 | 2025-07-07 | 25
| Apply Data Validation Techniques to Database | Abdallah El Sayed | 0% | 2025-07-07 | 2025-07-09 | 3
| Set up Spreadsheet Software Structure Featuring Raw and Manipulated Data | Abdallah El Sayed | 0% | 2025-06-13 | 2025-07-07 | 25
| Apply Data Validation Techniques to Spreadsheet | Abdallah El Sayed | 0% | 2025-07-07 | 2025-07-09 | 3
| Update and Submit any New Designs & Evaluation Critera | Abdallah El Sayed | 0% | 2025-07-07 | 2025-07-10 | 4
| Submit Test Plan Doc | Abdallah El Sayed | 0% | 2025-07-10 | 2025-07-13 | 4
| Document Development Processes and Contigencies for Solution | Abdallah El Sayed | 0% | 2025-07-13 | 2025-07-17 | 5
| Document all Evidence of Critical Thonksing | Abdallah El Sayed | 0% | 2025-07-17 | 2025-07-30 | 14
C7 Submit Final Infographic
| Select Preferred Annotated Design | Abdallah El Sayed | 0% | 2025-07-10 | 2025-07-29 | 20
| Apply Data Validation Techniques to Input Data | Abdallah El Sayed | 0% | 2025-07-30 | 2025-08-01 | 3
| Create and Input Data Visualisations | Abdallah El Sayed | 0% | 2025-08-01 | 2025-08-05 | 5
| Complete Detailing and Formatting of Final Infographic | Abdallah El Sayed | 0% | 2025-08-06 | 2025-08-12 | 7
C8 Implement File securing features
| Organise and Tag Files in Accordance to their Relation to their Tasks | Abdallah El Sayed | 100% | 2025-06-13 | 2025-06-16 | 4
| Install Github on Localised System | Abdallah El Sayed | 100% | 2025-06-16 | 2025-06-20 | 5
| Link Files Including Project To Github Online | Abdallah El Sayed | 100% | 2025-06-20 | 2025-07-05 | 16
| Push Github Origin and Fetch both Online and on Other Systems | Abdallah El Sayed | 100% | 2025-07-05 | 2025-07-24 | 20
| Maintain an Updated Backup of Project Files | Abdallah El Sayed | ~% | 2025-07-24 | 2025-07-24 | 1
| C9 Creating Evaluation Criteria |  |  |  | (criteria)
| Create Final Evaluation Criteria for Assessing Infographic Effectiveness | Abdallah El Sayed | 0% | 2025-08-12 | 2025-08-13 | 2
| Evaluate Infographic Effectiveness and Efficiency in Answering Research Question. | Abdallah El Sayed | 0% | 2025-08-13 | 2025-08-14 | 2
| Produce Final Evaluation Infographic & Dynamic Data Vis. | Abdallah El Sayed | 0% | 2025-08-14 | 2025-08-15 | 2
C10 Submit Completed Evaluation Criteria/Submit Final Assessment
| Review Entire Project | Abdallah El Sayed | 0% | 2025-08-16 | 2025-08-17 | 2
| Submit Final Assessment | Abdallah El Sayed | 0% | 2025-08-17 | 2025-08-19 | 3
| END OF PROJECT |  |  |  | 8/20/25
Monitor progress
Manage resources
Provide updates
Testing and validation
C4 Submit Raw and Cleansed Data
Monitor progress
Track expenses
Evaluate progress
Address risks
Gather feedback
C5 Submit Annotated Diagram/ etc. etc. etc. etc.
Define goals
Conduct studies
Establish comms
Develop charter
Set up team
SAT 2 BEGINNING
C6 Submit Spreadsheet/SQL/Database And Testplan/Validation
Create schedule
Identify deliverables
Develop budget
Define scope
Identify risks
C7 Submit Final Infographic
Execute tasks
Monitor progress
Manage resources
Provide updates
Testing and validation
C8 Submit a Report
Monitor progress
Track expenses
Evaluate progress
Address risks
Gather feedback
C10 Submit Completed Evaluation Criteria
Define goals
Conduct studies
Establish comms
Develop charter
Set up team
C2 Prepare a Gantt Chart
Create schedule
Identify deliverables
Develop budget
Define scope
Identify risks
END OF PROJECT
Formulas:
DON’T CHANGE THIS NUMBER = [DON’T CHANGE THIS NUMBER, row below]

## About
SIMPLE GANTT CHART by Vertex42.com
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. TimeSheet About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.