## Project schedule
| Europa project | [5 empty] | Project start: | [7 empty] | 2025-05-08
| VanArsdel, Ltd. | Project lead |  |  |  |  | Display week: | [7 empty] | 1
SIMPLE GANTT CHART by Vertex42.com
| https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html | [5 empty] | 2025-05-05 | [6 empty] | 2025-05-12 | [6 empty] | 2025-05-19 | [6 empty] | 2025-05-26 | [6 empty] | 2025-06-02 | [6 empty] | 2025-06-09 | [6 empty] | 2025-06-16 | [6 empty] | 2025-06-23 | [6 empty] | 2025-06-30 | [6 empty] | 2025-07-07 | [6 empty] | 2025-07-14 | [6 empty] | 2025-07-21 | [6 empty] | 2025-07-28 | [6 empty] | 2025-08-04 | [6 empty] | 2025-08-11 | [6 empty] | 2025-08-18
| Project stages | ASSIGNED TO | PROGRESS | START | END | time axis 2025-05-05 to 2025-08-24
 | time axis 2025-05-05 to 2025-08-24
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
| C1 Developing A Research Question |  |  |  | (criteria)
| Define goals | Abdallah El Sayed | 100% | 2025-05-08 | 2025-05-08 | 1
| Evaluate Research Topics | Abdallah El Sayed | 100% | 2025-05-08 | 2025-05-08 | 1
| Fill out C1 Table | Abdallah El Sayed | 100% | 2025-05-08 | 2025-05-09 | 2
C2 Prepare a Gantt Chart
| Create schedule | Abdallah El Sayed | 50% | 2025-05-09 | 2025-05-13 | 5 | bar: 2025-05-09 to 2025-05-13
| Identify deliverables | Abdallah El Sayed | 50% | 2025-05-11 | 2025-05-16 | 6
| Develop budget | Abdallah El Sayed |  | 2025-05-16 | 2025-05-19 | 4
| Define scope | Abdallah El Sayed |  | 2025-05-19 | 2025-05-22 | 4
| Identify risks | Abdallah El Sayed |  | 2025-05-19 | 2025-05-22 | 4
C3 Submit Analysis/Design Documentation of Project needs/requirements
| Execute tasks | Abdallah El Sayed | 50% | 2025-05-23 | 2025-05-28 | 6
| Monitor progress | Abdallah El Sayed | 60% | 2025-05-29 | 2025-06-02 | 5
| Manage resources | Abdallah El Sayed | 50% | 2025-06-03 | 2025-06-08 | 6
| Provide updates | Abdallah El Sayed | 25% | 2025-06-09 | 2025-06-13 | 5
| Testing and validation | Abdallah El Sayed | 25% | 2025-06-03 | 2025-06-07 | 5
C4 Submit Raw and Cleansed Data
| Monitor progress | Abdallah El Sayed | 25% | 2025-05-25 | 2025-05-28 | 4
| Track expenses | Abdallah El Sayed | 25% | 2025-05-28 | 2025-06-01 | 5
| Evaluate progress | Abdallah El Sayed | 50% | 2025-06-02 | 2025-06-05 | 4
| Address risks | Abdallah El Sayed | 60% | 2025-05-30 | 2025-06-02 | 4
| Gather feedback | Abdallah El Sayed | 50% | 2025-06-01 | 2025-06-06 | 6
C5 Submit Annotated Diagram/ etc. etc. etc. etc.
| Define goals | Abdallah El Sayed | 70% | 2025-05-08 | 2025-05-11 | 4
| Conduct studies | Abdallah El Sayed | 60% | 2025-05-11 | 2025-05-13 | 3
| Establish comms | Abdallah El Sayed | 50% | 2025-05-13 | 2025-05-17 | 5
| Develop charter | Abdallah El Sayed | 25% | 2025-05-17 | 2025-05-22 | 6
| Set up team | Abdallah El Sayed |  | 2025-05-12 | 2025-05-14 | 3
SAT 2 BEGINNING
C6 Submit Spreadsheet/SQL/Database And Testplan/Validation
| Create schedule | Abdallah El Sayed | 50% | 1899-12-31 | 1900-01-04 | 5
| Identify deliverables | Abdallah El Sayed | 50% | 1900-01-02 | 1900-01-07 | 6
| Develop budget | Abdallah El Sayed |  | 1900-01-07 | 1900-01-10 | 4
| Define scope | Abdallah El Sayed |  | 1900-01-07 | 1900-01-09 | 3
| Identify risks | Abdallah El Sayed |  | 1900-01-07 | 1900-01-10 | 4
C7 Submit Final Infographic
| Execute tasks | Abdallah El Sayed | 50% | 2025-05-26 | 2025-05-31 | 6
| Monitor progress | Abdallah El Sayed | 60% | 2025-06-01 | 2025-06-05 | 5
| Manage resources | Abdallah El Sayed | 50% | 2025-06-06 | 2025-06-11 | 6
| Provide updates | Abdallah El Sayed | 25% | 2025-06-12 | 2025-06-16 | 5
| Testing and validation | Abdallah El Sayed | 25% | 2025-06-06 | 2025-06-10 | 5
C8 Submit a Report
| Monitor progress | Abdallah El Sayed | 25% | 2025-05-28 | 2025-05-31 | 4
| Track expenses | Abdallah El Sayed | 25% | 2025-05-31 | 2025-06-04 | 5
| Evaluate progress | Abdallah El Sayed | 50% | 2025-06-05 | 2025-06-08 | 4
| Address risks | Abdallah El Sayed | 60% | 2025-06-02 | 2025-06-05 | 4
| Gather feedback | Abdallah El Sayed | 50% | 2025-06-04 | 2025-06-09 | 6
| C10 Submit Completed Evaluation Criteria |  |  |  | (criteria)
| Define goals | Abdallah El Sayed | 70% | 2025-05-08 | 2025-05-11 | 4
| Conduct studies | Abdallah El Sayed | 60% | 2025-05-11 | 2025-05-13 | 3
| Establish comms | Abdallah El Sayed | 50% | 2025-05-13 | 2025-05-17 | 5
| Develop charter | Abdallah El Sayed | 25% | 2025-05-17 | 2025-05-22 | 6
| Set up team | Abdallah El Sayed |  | 2025-05-12 | 2025-05-14 | 3
C2 Prepare a Gantt Chart
| Create schedule | Abdallah El Sayed | 50% | 2025-05-13 | 2025-05-17 | 5
| Identify deliverables | Abdallah El Sayed | 50% | 2025-05-15 | 2025-05-20 | 6
| Develop budget | Abdallah El Sayed |  | 2025-05-20 | 2025-05-23 | 4
| Define scope | Abdallah El Sayed |  | 2025-05-20 | 2025-05-22 | 3
| Identify risks | Abdallah El Sayed |  | 2025-05-20 | 2025-05-23 | 4
| END OF PROJECT |  |  |  | 7/28/25
C2 Prepare a Gantt Chart
[119 empty] | Create schedule | Abdallah El Sayed | 50% | 1899-12-31 | 1900-01-04
[119 empty] | Identify deliverables | Abdallah El Sayed | 50% | 1900-01-02 | 1900-01-07
[119 empty] | Develop budget | Abdallah El Sayed |  | 1900-01-07 | 1900-01-10
[119 empty] | Define scope | Abdallah El Sayed |  | 1900-01-07 | 1900-01-09
[119 empty] | Identify risks | Abdallah El Sayed |  | 1900-01-07 | 1900-01-10
C3 Submit Analysis/Design Documentation of Project needs/requirements
[119 empty] | Execute tasks | Abdallah El Sayed | 50% | 1900-01-14 | 1900-01-19
[119 empty] | Monitor progress | Abdallah El Sayed | 60% | 1900-01-20 | 1900-01-24
[119 empty] | Manage resources | Abdallah El Sayed | 50% | 1900-01-25 | 1900-01-30
[119 empty] | Provide updates | Abdallah El Sayed | 25% | 1900-01-31 | 1900-02-04
[119 empty] | Testing and validation | Abdallah El Sayed | 25% | 1900-01-25 | 1900-01-29
C4 Submit Raw and Cleansed Data
[119 empty] | Monitor progress | Abdallah El Sayed | 25% | 1900-01-16 | 1900-01-19
[119 empty] | Track expenses | Abdallah El Sayed | 25% | 1900-01-19 | 1900-01-23
[119 empty] | Evaluate progress | Abdallah El Sayed | 50% | 1900-01-24 | 1900-01-27
[119 empty] | Address risks | Abdallah El Sayed | 60% | 1900-01-21 | 1900-01-24
[119 empty] | Gather feedback | Abdallah El Sayed | 50% | 1900-01-23 | 1900-01-28
C5 Submit Annotated Diagram/ etc. etc. etc. etc.
[119 empty] | Define goals | Abdallah El Sayed | 70% | 2025-05-08 | 2025-05-11
[119 empty] | Conduct studies | Abdallah El Sayed | 60% | 2025-05-11 | 2025-05-13
[119 empty] | Establish comms | Abdallah El Sayed | 50% | 2025-05-13 | 2025-05-17
[119 empty] | Develop charter | Abdallah El Sayed | 25% | 2025-05-17 | 2025-05-22
[119 empty] | Set up team | Abdallah El Sayed |  | 2025-05-12 | 2025-05-14
SAT 2 BEGINNING
C6 Submit Spreadsheet/SQL/Database And Testplan/Validation
[119 empty] | Create schedule | Abdallah El Sayed | 50% | 1899-12-31 | 1900-01-04
[119 empty] | Identify deliverables | Abdallah El Sayed | 50% | 1900-01-02 | 1900-01-07
[119 empty] | Develop budget | Abdallah El Sayed |  | 1900-01-07 | 1900-01-10
[119 empty] | Define scope | Abdallah El Sayed |  | 1900-01-07 | 1900-01-09
[119 empty] | Identify risks | Abdallah El Sayed |  | 1900-01-07 | 1900-01-10
C7 Submit Final Infographic
[119 empty] | Execute tasks | Abdallah El Sayed | 50% | 2025-05-26 | 2025-05-31
[119 empty] | Monitor progress | Abdallah El Sayed | 60% | 2025-06-01 | 2025-06-05
[119 empty] | Manage resources | Abdallah El Sayed | 50% | 2025-06-06 | 2025-06-11
[119 empty] | Provide updates | Abdallah El Sayed | 25% | 2025-06-12 | 2025-06-16
[119 empty] | Testing and validation | Abdallah El Sayed | 25% | 2025-06-06 | 2025-06-10
C8 Submit a Report
[119 empty] | Monitor progress | Abdallah El Sayed | 25% | 2025-05-28 | 2025-05-31
[119 empty] | Track expenses | Abdallah El Sayed | 25% | 2025-05-31 | 2025-06-04
[119 empty] | Evaluate progress | Abdallah El Sayed | 50% | 2025-06-05 | 2025-06-08
[119 empty] | Address risks | Abdallah El Sayed | 60% | 2025-06-02 | 2025-06-05
[119 empty] | Gather feedback | Abdallah El Sayed | 50% | 2025-06-04 | 2025-06-09
[119 empty] | C10 Submit Completed Evaluation Criteria |  |  |  | (criteria)
[119 empty] | Define goals | Abdallah El Sayed | 70% | 2025-05-08 | 2025-05-11
[119 empty] | Conduct studies | Abdallah El Sayed | 60% | 2025-05-11 | 2025-05-13
[119 empty] | Establish comms | Abdallah El Sayed | 50% | 2025-05-13 | 2025-05-17
[119 empty] | Develop charter | Abdallah El Sayed | 25% | 2025-05-17 | 2025-05-22
[119 empty] | Set up team | Abdallah El Sayed |  | 2025-05-12 | 2025-05-14
C2 Prepare a Gantt Chart
[119 empty] | Create schedule | Abdallah El Sayed | 50% | 2025-05-13 | 2025-05-17
[119 empty] | Identify deliverables | Abdallah El Sayed | 50% | 2025-05-15 | 2025-05-20
[119 empty] | Develop budget | Abdallah El Sayed |  | 2025-05-20 | 2025-05-23
[119 empty] | Define scope | Abdallah El Sayed |  | 2025-05-20 | 2025-05-22
[119 empty] | Identify risks | Abdallah El Sayed |  | 2025-05-20 | 2025-05-23
[119 empty] | END OF PROJECT |  |  |  | 7/28/25
Formulas:
Display week: = [Display week:, row below]

## About
SIMPLE GANTT CHART by Vertex42.com
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. TimeSheet About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.